## React_Automation_Feasibility
S.no | Userflow | Title | Priority | ADO State | Sub Status | PBI ID | Automation Feasibiity Yes / No | Assigned To | # No of test cases | Planned Dates |  | Automation Scripting | Automatable Test cases | Inprogress | Completed | Visual Coverage | Manual test cases | Comments
1 | My Programs | Closed program | Priority3 | Committed | 16_Under Triage | 140509 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
2 | My Programs | Open Programs - Program Card for Upcoming program user has not enrolled in | Priority1 | Committed | 03_Ready for Dev | 140485 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
3 | My Programs | Open Programs - Program Card for Ongoing program user has not enrolled in | Priority1 | Committed | 03_Ready for Dev | 140484 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
4 | My Programs | Open programs screen with no program | Priority1 | Committed | 03_Ready for Dev | 140483 | Yes | Sankar | 6 |  |  | Completed |  |  | 6 |  | 0
5 | My Programs | Hide upcoming programs section when no upcoming program is available | Priority1 | Committed | 03_Ready for Dev | 140482 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
6 | My Programs | Hide ongoing programs section when no ongoing program is available | Priority1 | Committed | 03_Ready for Dev | 140481 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
7 | My Programs | Open Programs screens | Priority1 | Committed | 03_Ready for Dev | 140480 | No | Sankar | 3 | [7 empty] | 3 | lazy load and Theme checking
8 | My Programs | My Programs - Program Card for Closed program user had enrolled in | Priority3 | Committed | 03_Ready for Dev | 140479 | No | Sankar | 3 | [7 empty] | 3 | Program Progress checking
9 | My Programs | My Programs - Program Card for Upcoming program user has enrolled in | Priority3 | Committed | 03_Ready for Dev | 140478 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
10 | My Programs | Program overall progress | Priority3 | Committed | 03_Ready for Dev | 140477 | No | Sankar | 3 | [7 empty] | 3 | Checking the reading Progress
11 | My Programs | My Programs - Program Card for Ongoing program user has enrolled in | Priority3 | Committed | 03_Ready for Dev | 140476 | No | Sankar | 3 | [7 empty] | 3 | Program Progress Checking
12 | My Programs | My programs screen with no program | Priority3 | Committed | 03_Ready for Dev | 140475 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
13 | My Programs | Hide closed programs section when no closed program for the user | Priority3 | Committed | 03_Ready for Dev | 140474 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
14 | My Programs | Hide active programs section when no active program enrolled in | Priority3 | Committed | 03_Ready for Dev | 140473 | Yes | Sankar | 3 |  |  | Completed |  |  | 3 |  | 0
15 | My Programs | My Programs screens | Priority3 | Committed | 03_Ready for Dev | 140472 | No | Sankar | 3 | [7 empty] | 3 | lazy load and Theme checking
16 | My Programs | Navigation to Programs screens from Bottom navigation bar or My shelf screen | Priority3 | Committed | 03_Ready for Dev | 140471 | No | Sankar | 7 | [7 empty] | 7 | Theme Checking
17 | My Stuff - All Screen | Search within Checkouts, Holds, Recommendations, Wishlist, History and Downloads screen | Priority19 | Approved | 02_Feature File Review | 139171 | Yes | Sankar | 7 |  |  | Completed |  |  | 6 |  | 1 | Theme Checking
20 | My Stuff - All Screen | Filter titles on Checkouts, Holds, Wishlist, Recommended and Checkout History screen [TO BE UPDATED] | Priority19 | New | 02_Feature File Review | 139167 | Yes | Sankar | 6 |  |  | Completed |  |  | 5 |  | 1 | Theme Checking
21 | My Stuff - All Screen | View quick navigation CTAs for Checkouts, Holds, Wishlist, Recommendations, Checkout History and Downloads screen | Priority18 | Committed | 02_Feature File Review | 139166 | Yes | Sankar | 7 |  |  | Completed |  |  | 6 |  | 1 | UI Checking
22 | My Stuff - All Screen | Do not show quick navigation CTA for history screen | Priority18 | Committed | 02_Feature File Review | 139165 | Yes | Sankar | 10 |  |  | Completed |  |  | 10 |  | 0
23 | Wishlist | Grid view for Wishlist screen | Priority8 | Committed | 03_Ready for Dev | 139144 | No | Sankar | 7 | [5 empty] | 0 |  | 7 | Cover Image checking
24 | Wishlist | Title from Wishlist is removed on checkout | Priority7 | Committed | 03_Ready for Dev | 139143 | yes | Kothandan | 6 |  |  | Completed |  |  | 6 |  | 0
25 | Wishlist | Sort titles on Wishlist screen | Priority8 | Committed | 03_Ready for Dev | 139142 | yes | Kothandan | 8 |  |  | Completed |  |  | 8 |  | 0
26 | Wishlist | Wishlist screen list view | Priority7 | Committed | 03_Ready for Dev | 139141 | No | Sankar | 7 | [5 empty] | 0 |  | 7 | Cover Image checking
27 | Wishlist | Wishlist screen no title added to Wishlist | Priority7 | Committed | 03_Ready for Dev | 139139 | No | Sankar | 3 |  |  |  | 0 |  |  |  | 3 | Theme Checking
28 | Wishlist | Wishlist screen profile based | Priority7 | Committed | 04_Dev In Progress | 139138 | No | Sankar | 9 |  |  |  | 0 |  |  |  | 9 | Theme Checking
29 | Checkouts | Grid view for checkout screen | Priority3 | Committed | 03_Ready for Dev | 139126 | No | Sankar | 7 |  |  |  | 0 |  |  |  | 7 | UI and Theme Checking
30 | Checkouts | Access checkouts screen when offline/no internet | Priority3 | Committed | 03_Ready for Dev | 139125 | No | Sankar | 13 |  |  |  | 0 |  |  |  | 13 | Offline Scenarios
31 | Checkouts | Sort titles on Checkouts screen | Priority2 | Committed | 03_Ready for Dev | 139124 | Yes | Sankar | 10 |  |  | Completed | 9 |  |  |  | 1 | Theme Checking
32 | Checkouts | Checkout screen list view | Priority2 | Committed | 03_Ready for Dev | 139123 | No | Sankar | 7 |  |  |  | 0 |  |  |  | 7 | Theme Checking
33 | Checkouts | Checkout screen no title checked out | Priority1 | Committed | 03_Ready for Dev | 139122 | Yes | Sankar | 4 |  |  | Completed | 3 |  |  |  | 1 | UI Checking
34 | Checkouts | Checkout screen profile based | Priority1 | Committed | 03_Ready for Dev | 139121 | Yes | Sankar | 13 |  |  | Completed | 12 |  |  |  | 1 | UI Checking
35 | Notifications | Firebase notifications in notification details view | Priority2 | New | 16_Under Triage | 133877 | Yes | Kothandan | 12 |  |  |  | 9 |  |  |  | 3
36 | Notifications | Firebase notifications in notification screen (i.e. current notifications populated in native Menu>Announcement section) | Priority2 | New | 00_Not Started | 133876 | Yes | Kothandan | 12 |  |  |  | 9 |  |  |  | 3
37 | Notifications | Delete Confirmation | Priority1 | Approved | 03_Ready for Dev | 133875 | Yes | Kothandan | 18 |  |  |  | 18 |  |  |  | 0
38 | Notifications | Edit screen - Delete selected notifications | Priority1 | Approved | 03_Ready for Dev | 133871 | Yes | Kothandan | 9 |  |  |  | 6 |  |  |  | 3
39 | Notifications | Edit screen - Mark Menu Options and actions | Priority1 | Approved | 03_Ready for Dev | 133870 | Yes | Kothandan | 18 |  |  |  | 15 |  |  |  | 3
40 | Notifications | Edit screen - select multiple notification | Priority1 | Approved | 03_Ready for Dev | 133869 | Yes | Sankar | 33 |  |  | Completed |  |  | 30 |  | 3
41 | Notifications | Mark as read/unread and delete notification actions on left swipe | Priority1 | Approved | 03_Ready for Dev | 133868 | Yes | Sankar | 18 |  |  | Completed |  |  | 18 |  | 0
42 | Notifications | Notification center edit screen navigation | Priority1 | Approved | 01_Ready for Feature File | 133867 | Yes | Sankar | 4 |  |  | Completed |  |  | 3 |  | 1
43 | Notifications | Notification center landing screen | Priority1 | Committed | 03_Ready for Dev | 133866 | Yes | Sankar | 18 |  |  |  | 12 |  |  |  | 6
44 | Notifications | Notification center icon | Priority1 | Approved | 02_Feature File Review | 133865 | Yes | Sankar | 18 |  |  |  |  | 15 |  |  | 3
45 | My Profile-Settings | Interest survey CTA in my profile | Priority4 | Committed | 03_Ready for Dev | 132819 | Yes | Sankar | 4 |  |  | Completed |  |  | 3 |  | 1
46 | My Profile-Settings | Confirmation on changing profile type and message for reset of interest survey | Priority5 | Approved | 02_Feature File Review | 132251 | Yes | Sankar | 10 |  |  | Completed |  |  | 8 |  | 2
47 | Interest Survey | Reset interest survey when profile type is changed | Priority1 | Committed | 05_Code Review | 132101 | Yes | Sankar | 2 |  |  | Completed |  |  | 2 |  | 0
48 | Interest Survey | Update interests preference | Priority1 | Committed | 05_Code Review | 132100 | Yes | Sankar | 6 |  |  | Completed |  |  | 4 |  | 2
49 | Interest Survey | Interest Survey pop-up on first login of the month when preference is not set | Priority1 | Committed | 05_Code Review | 132099 | No |  | 5 | [7 empty] | 5
50 | Interest Survey | Interest Survey when user logs in for first time | Priority1 | Committed | 05_Code Review | 132098 | No |  | 3 | [7 empty] | 3
51 | Interest Survey-Kids | Interests survey topics for Kid | Priority3 | Committed | 05_Code Review | 132097 | No |  | 2 | [7 empty] | 2
52 | Interest Survey-Teens | Interests survey topics for Teen | Priority2 | Committed | 05_Code Review | 132096 | No |  | 2 | [7 empty] | 2
53 | Interest Survey | Interests survey topics for Adult when library has KidsZone subscription only | Priority1 | Committed | 05_Code Review | 132095 | No |  | 2 | [7 empty] | 2
54 | Interest Survey | Interests survey topics for Adult when library has Axis360 subscription | Priority1 | Committed | 05_Code Review | 132094 | Yes | Sankar | 2 |  |  | Completed |  |  | 1 |  | 1
55 | Interest Survey | Interest survey screen based on library subscription and profile type | Priority1 | Committed | 05_Code Review | 132093 | No |  | 11 | [7 empty] | 11
56 | Interest Survey | Navigation to Interest Survey screen | Priority1 | Committed | 04_Dev In Progress | 132092 | Yes | Sankar | 1 |  |  | Completed |  |  | 1 |  | 0
57 | My Profile | My Profile of Adult Patron | Priority1 | Committed | 03_Ready for Dev | 124474 | Yes | Kothandan | 4 |  |  | Completed |  |  | 2 |  | 2 | UI Cases
[9 empty] | 393 | 0 | 0 | 0 | 93 | 15 | 146 |  | 139

## ReactAutomation Summary
[9 empty] | Automation Feasibiity Yes / No | Yes
Automation Summary_RNative
Sprint | # of TC | Automatable | Automated TC's |  |  | Automation% | Non Automatable | Review Status | Row Labels | Sum of # No of test cases | Sum of Automatable Test cases - Not Started | Sum of Automatable Test cases - In-Progress | Sum of Automatable Test cases - Completed | Sum of Manual test cases
|  |  | Not Started | In-Progress | Completed |  |  |  | Checkouts | 27 | 24 |  |  | 3
Sprint 4a | 138 | 85 | 0 | 0 | 85 | 61.59% | 53 |  | Interest Survey | 11 | 8 |  |  | 3
[9 empty] | My Profile | 4 | 2 |  |  | 2
[5 empty] | 100% |  |  |  | My Profile-Settings | 14 | 11 |  |  | 3
[9 empty] | My Programs | 42 | 12 | 15 | 15 | 0
[9 empty] | My Stuff - All Screen | 30 | 27 |  |  | 3
[9 empty] | Notifications | 160 | 135 |  |  | 25
[9 empty] | Wishlist | 14 | 14 |  |  | 0
[9 empty] | Grand Total | 302 | 233 | 15 | 15 | 39
[9 empty] | # No of test cases | Not Started | In-Progress | Completed
[9 empty] | 263 | 233 | 15 | 15
[9 empty] | - | 88.59% | 5.703% | 5.703%

## Scripting and Execution Status
SCRIPTING STATUS - SPRINT 4B | [8 empty] | EXECUTION SUMMARY STATUS
Userflow | # Total Scope of PBI's | NFR and ADA (OOS) | Only Automation PBI's | Automation test Cases | Total Completed | In-Progress |  |  | Platform | # TCs in Automation | Total Executed | Pass | Fail | Not Executed | Blocked | % Executed | % Pass | % Fail
My Programs | 16 | 0 | 13 | 33 | 33 | 0 |  |  | iOS build # 10.0.0.75 | 95 | 95 | 81 | 14 | 0 | 0 | 100% | 85.26% | 14.74%
My Stuff | 9 | 0 | 4 | 27 | 27 | 0 |  |  | Android build # 10.0.0.88 | 95 | 95 | 84 | 11 | 0 | 0 | 100% | 88.42% | 11.58%
Checkouts | 6 | 0 | 3 | 19 | 19 | 0
Interest Survey | 10 | 0 | 6 | 19 | 19 | 0
Total | 41 | 0 | 26 | 98 | 98 | 0
[9 empty] | Platform | Sum of # TCs in Automation | Sum of Pass | Sum of Fail
Userflow | Sum of Automation test Cases | Sum of Total Completed | Sum of In-Progress | [5 empty] | iOS build # 10.0.0.75 | 98 | 81 | 14
Checkouts | 19 | 19 | 0 | [5 empty] | Android build # 10.0.0.88 | 98 | 84 | 11
Interest Survey | 19 | 19 | 0 | [5 empty] | Grand Total | 196 | 165 | 25
My Programs | 33 | 33 | 0
My Stuff | 27 | 27 | 0
Grand Total | 98 | 98 | 0
|  |  |  | Platform | # of Scenarios failed | Classification of Failures
[6 empty] | Functional issue / Performance | Script Issue/Test Data | Locator issues / Comments
|  |  |  | Android | 16 | 1 Defect raised for functional and impacted 3 failures | 10 | 3 issues are due to locator changes
|  |  |  | iOS | 19 | 1 Defect raised for functional and impacted 3 failures | 4 | Two defects Raised for Locator changes and impacted 12 failures
0

## Regression Automation
Userflow | Title | User flow | Manual Regression | PBI ID
|  | Library page_widget display | User should be able to view the Magazines (from third party) as carousel on landing screen
User should be able to tap on any category and should navigate to content list page for that category
User should be able to click on the title or image of the content in the list to view the detailed page
Verify currently reading widget so that I should be able to see the 3rd party content render in the widget
Content(from third party) to be displayed is configured as widget in Admin settings
User should be able to view the currently reading section as Learning link widget
User should be able to click on read now to read the content in web browser in mobile or in app as pop up
User should be able to view the tier page based on the configuration set in CMS
|  | Pages(Tier 1/2/3) | User should be navigated to the Tier 1 Page configured for the widget
User should be able to view the Tier 1 Page as defined in the CMS
User should be navigated to the Tier 2 Page configured for the widget
User should be able to view the Tier and 2 Page as defined in the CMS
User should be navigated to the Tier 3 Page configured for the widget
User should be able to view the Tier 3 Page as defined in the CMS
User should be able to view Interest survey screen/pop-up with Adult theme and topics when profile type is Adult and library has kids zone and Axis 360 subscription
|  | Interest Survey | User should be able to view Interest survey screen/pop-up with teen theme and topics when profile type is Adult and library has kid.s zone subscription only | 132092
|  |  | User should be able to view Interest survey screen/pop-up with kid theme and topics when profile type is kid and library has kids zone subscription | 132092
|  |  | User should be able to view Interest survey screen/pop-up with teen theme and topics when profile type is teen and library has kids zone subscription | 132092
|  |  | Axis360 subscription - User should be able to view interest topics for Adult and view preferred age level options Juvenile, Young Adult and Adult | 132094
|  |  | KidsZone subscription only - User should be able to view interest topics for adult and able to view preferred age level options Kid (Currently: Juvenile) and Teen (Currently: Young Adult) | 132094
|  |  | User should be able to view interest topics for Teen and able to view preferred age level options Kid (Currently: Juvenile) and Teen (Currently: Young Adult) | 132094
|  |  | User should be able to view interest topics for Kid and Kid (Currently: Juvenile) option should be auto selected and non editable | 132819
|  |  | User should be able to view Interest Survey topics based on library subscription and user profile type | 132819
|  |  | User should be able to select the interest icons and submit the preference by clicking save CTA | 132819
User should not be able to view interest survey pop up when recommendations flag is disabled for the library​ or certain profile type by the Admin
|  |  | Interest Survey pop-up on first login of the month when preference is not set | 132251
|  |  | Update interests preference | 132100
|  |  | Reset interest survey when profile type is changed | 132101
User should be able to navigate to Title Details screen by clicking title image in updated title widget for eBook
|  | Title Widget | User should be able to navigate to Title Details screen by clicking title image in updated title widget for Audio Book
User should be able to view and click see all CTA and navigate to Newspapers & Magazines list screen
|  | Carousel | User should be able to see the count of unread notifications on bell icon for that user
|  | Notification | User should be able to view ‘No Notifications available’ text in place of the notification listing if there are no notifications available for the user​
|  |  | User should be able to view unread notifications grouped on top followed by read notifications grouped below unread notification | 133870
User should be able to view notifications sorted by received date and time with latest notification first within unread and read group
User should be able to view the notifications in lazy loading fashion when user scrolls through the notifications – 20 notifications displayed at a time
|  |  | User should be able to tap on edit CTA and navigate to notification edit screen | 133867
Application should not display any deleted notification in the notification list​
|  |  | User should be able to view Mark as read/unread and delete option only for the latest notification swiped left | 133875
|  |  | User should be able to view the detail of the notifications by clicking the notification | 133866
User should be able to view notifications sorted by received date and time with latest notification first within unread and read group
|  | Firebase notifications | User should be able to view notification marked as read when user navigates back to Notification screen from notification details screen​ | 133877
User should be able to view filter and sort option for the titles
|  | Checkouts | User should be able to click on List/Grid view icon to switch been list view and grid view | 139124
Adult patron with teen and kid profiles mapped should not be able to view the checked out titles for these users in checkout screen
|  |  | User should be able to view no title checked out screen | 139122
User should be able to view number of days remaining for title return/checkout expiry
User should be able to view number of hours remaining (24 hrs or less) for title return/checkout expiry when only one day is left
User should be able to view reading progress of the title as a progress bar and percentage on the card
User should be able to view download progress during downloading title and cancel CTA to cancel download and pause CTA to pause
|  |  | User should be able to view sort options: Latest Checkout, Due Date, A-Z | 139124
System should save the user reading progress, bookmarks, highlights and notes in offline mode and sync back to server once application is back online
User should be able to view titles added to Wishlist by that user only
|  | Wishlist | User should be able to click on List/Grid view icon to switch been list view and grid view | 139142
User should be able to view Wishlist screen with theme rendered based on library subscription and user profile type
|  |  | User should be able to view primary action for the title as a button | 139143
|  |  | User should not be able to view History CTA in the top quick navigation CTA carousel | 139143
|  | My Stuff | User able to navigate to Checkouts, Holds, Wishlist, Recommendations, Checkout History and Downloads screen | 139171
|  |  | User should be able to view titles filtered based on options selected | 139167
User should be able to click on "Continue" and navigate to erader/audio player of the title to the last read/listened location
User should be able to click on "Read Online" and navigate to ereader online
User should be able to click on "Listen Now" and navigate to audioplayer online
User should be able to click on "Read Now" and navigate to eareder for the downloaded title
User should be able to click on "Continue" and navigate to erader/audio player of the title to the last read/listened location
User should be able to view the pop-up to confirm for the actions: Return, Renew, Remove (Delete Download), Remove (From checkout history
User should be able to view the results based on search keyword from the titles checked out, Titles on hold, Titles recommended, Titles in Wishlist, Titles in history and titles/publications downloaded
Verify user able to view My Programs and Open Programs screen with theme rendered based on library subscription and user profile type
|  | My Programs | User should not be able to view the programs that user left
|  |  | User able to view all state programs ongoing, upcoming and closed programs | 140509
|  |  | User should be able to click on all state programs card and navigate to program details screen | 140485
User should be able to view overall progress of the program as a progress bar
User should be able to view number of participants for the program
User should be able to view progress calculated based on completion of the titles in the reading program
Application should not update the program progress once program has closed (i.e. end date passed)
User should be able to click on "Continue" and navigate to erader/audio player of the title to the last read/listened location
System should remove user from the closed program
|  |  | Verify hide active programs section when no active program enrolled in | 140481
|  |  | Verify User able to view screen for no program to be displayed for the user in the my programs tab | 140481
|  |  | User should be able to view ongoing programs that user is not participating in listed under ongoing programs section | 140484
|  | Open Programs | User should be able to view upcoming programs that user is not participating in listed under upcoming programs section | 140483
|  |  | User should be able to click on programs card and navigate to program details screen | 140478
|  |  | User should not be able to view ongoing programs section when no ongoing program is available for that user profile | 140473
|  |  | Open programs screen with no program | 140475
User should be able to view Title Details screen with theme rendered based on library subscription and user profile type
|  | Details Page | User should be able to view subtitle of an eBook Book if available
User should be able to view subtitle of an Audio Book if available
User should not be able to view the reading progress if insights preferences are disabled in the user preferences
User should be able to view Primary Action, Wishlist CTA and Share CTA when title has only one action available other than add/remove to Wishlist and Share
User should be able to view the confirmation toast message for adding and removing title from the Wishlist
User should be able to view error message if sharing is failed
Verify user able to view following book details ISBN, Publisher, Released, Language & Age Level - eBook & Audio Book
User should not view the available copies attribute if no copy is available for checkout
User should be able to view Patrons on Hold count for the title (Existing logic to be used)
User should be able to view Level 1 and Level 2 subjects mapped to the title based on BISAC
User should be able to view "No Recommended books available" displayed if no title to be recommended
User should be able to view rating based on average of ratings input for that title by the patrons of that library
|  | Ratings and review | System should only show approved ratings and calculate average rating based on the approved ratings only
System should submit the rating to library admin for approval
User should be able to view the message for rating that has not been approved by Admin
User should be able to submit the review by clicking Submit CTA

## Reports_Android
My Programs
Date: 13/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Hide active programs section when no active program enrolled in -Reactnative | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:10 | Passed
| Hide closed programs section when no closed program for the user -Reactnative | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:07 | Passed
| My programs screen with no program -Reactnative | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:08 | Passed
| My Programs - Program Card for Upcoming program user has enrolled in -Reactnative | 20 | 3 | 16 | 0 | 0 | 39 | 0 | 3 | 3 | 0:10 | Failed
| Closed program -Reactnative | 21 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 3 | 0:08 | Passed
|  | 113 | 3 | 16 | 0 | 0 | 132 | 12 | 3 | 15 | 0:42 | 5
|  | 85.61% | 2.27% | 12.12% | 0% | 0% |  | 80% | 20% |  |  | 80%
Checkouts
Date: 13/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Adult user is able to View Checkout screen and titles based on profile | 60 | 0 | 0 | 0 | 0 | 60 | 5 | 0 | 5 | 0:06 | Passed
| Kid User is able to View Checkout screen and titles based on profile | 46 | 0 | 0 | 0 | 0 | 46 | 4 | 0 | 4 | 0:09 | Passed
| Teen user is able to View Checkout screen and titles based on profile | 46 | 0 | 0 | 0 | 0 | 46 | 4 | 0 | 4 | 0:09 | Passed
| View No titles in checkouts screen based on profile | 20 | 1 | 3 | 0 | 0 | 24 | 2 | 1 | 3 | 0:07 | Failed
| Adult user is able to view sort options and sort titles on the Checkouts screen | 30 | 0 | 0 | 0 | 0 | 30 | 3 | 0 | 3 | 0:07 | Passed
|  | 202 | 1 | 3 | 0 | 0 | 206 | 18 | 1 | 19 | 0:38 | 5
|  | 98.06% | 0.49% | 1.46% | 0% | 0% |  | 94.74% | 5.26% |  |  | 80%
Open Programs | 16/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Hide ongoing programs section when no ongoing program is available | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:10 | Passed
| Hide upcoming programs section when no upcoming program is available | 27 | 0 | 0 | 0 | 0 | 27 | 3 | 0 | 3 | 0:08 | Passed
| Open programs screen with no program | 51 | 0 | 0 | 0 | 0 | 54 | 6 | 0 | 6 | 0:15 | Passed
| Open Programs - Program Card for Ongoing program user has not enrolled in | 33 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 3 | 0:12 | Passed
| Open Programs - Program Card for Upcoming program user has not enrolled in | 20 | 0 | 0 | 0 | 0 | 33 | 2 | 0 | 3 | 0:08 | Passed
|  | 155 | 0 | 0 | 0 | 0 | 177 | 18 | 0 | 18 | 0:53 | 5
|  | 100% | 0% | 0% | 0% | 0% |  | 100% | 0% |  |  | 100%
Interest Survey | 17/08/2022
| Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Navigation to Interest Survey screen | 7 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 1 | 0:05 | Passed
| Interests survey topics for Adult when library has Axis360 subscription | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0:04 | Passed
| Update interests preference | 24 | 0 | 0 | 0 | 0 | 25 | 3 | 0 | 4 | 0:11 | Passed
| Reset interest survey when profile type is changed | 18 | 0 | 0 | 0 | 0 | 18 | 2 | 0 | 2 | 0:08 | Passed
| Confirmation on changing profile type and message for reset of interest survey | 72 | 0 | 0 | 0 | 0 | 72 | 8 | 0 | 8 | 0:33 | Passed
| Interest survey cta in my profile screen | 21 | 0 | 0 | 0 | 0 | 27 | 1 | 0 | 3 | 0:07 | Passed
|  | 151 | 0 | 0 | 0 | 0 | 158 | 19 | 0 | 19 | 1:07 | 6
|  | 100% | 0% | 0% | 0% | 0% |  | 100% | 0% |  |  | 100%
24/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| My Profile of Adult Patron | 6 | 0 | 0 | 0 | 0 | 23 | 2 | 0 | 2 | 0:02 | Passed
| Navigation to Interest Survey screen | 7 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 1 | 0:02 | Passed
| Interests survey topics for Adult when library has Axis360 subscription | 6 | 1 | 2 | 0 | 0 | 9 | 0 | 1 | 1 | 0:05 | Failed
| Update interests preference | 19 | 1 | 5 | 0 | 0 | 25 | 2 | 2 | 4 | 0:14 | Failed
| Reset interest survey when profile type is changed | 6 | 2 | 10 | 0 | 0 | 18 | 0 | 2 | 2 | 0:04 | Failed
| Confirmation on changing profile type and message for reset of interest survey | 38 | 0 | 0 | 0 | 0 | 71 | 8 | 0 | 8 | 0:21 | Passed
| Interest survey cta in my profile screen | 12 | 3 | 12 | 0 | 0 | 27 | 2 | 1 | 3 | 0:06 | Failed
| Adult user is able to View Checkout screen and titles based on profile | 42 | 3 | 15 | 0 | 0 | 60 | 2 | 3 | 5 | 0:07 | Failed
| Kid User is able to View Checkout screen and titles based on profile | 25 | 3 | 18 | 0 | 0 | 46 | 1 | 3 | 4 | 0:08 | Failed
| Teen user is able to View Checkout screen and titles based on profile | 40 | 1 | 5 | 0 | 0 | 46 | 3 | 1 | 4 | 0:09 | Failed
| View No titles in checkouts screen based on profile | 16 | 1 | 7 | 0 | 0 | 24 | 2 | 1 | 3 | 0:04 | Failed
| Adult user is able to view sort options and sort titles on the Checkouts screen | 15 | 0 | 0 | 0 | 0 | 30 | 3 | 0 | 3 | 0:04 | Passed
| Do not show quick navigation CTA for history screen | 33 | 5 | 12 | 0 | 0 | 50 | 8 | 2 | 10 | 0:07 | Failed
| View quick navigation CTAs for Checkouts, Holds, Wishlist, Recommendations, Checkout History and Downloads screen | 30 | 0 | 0 | 0 | 0 | 30 | 6 | 0 | 6 | 0:06 | Passed
| Filter titles on Checkouts, Holds, Wishlist, Recommended and Checkout History screen [TO BE UPDATED] | 24 | 0 | 0 | 0 | 0 | 45 | 5 | 0 | 5 | 0:08 | Passed
| Search within Checkouts, Holds, Recommendations, Wishlist, History and Downloads screen | 21 | 0 | 0 | 0 | 0 | 42 | 6 | 0 | 6 | 0:07 | Passed
| Hide active programs section when no active program enrolled in -Reactnative | 12 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:07 | Passed
| Hide closed programs section when no closed program for the user -Reactnative | 18 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:11 | Passed
| My programs screen with no program -Reactnative | 12 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:08 | Passed
| My Programs - Program Card for Upcoming program user has enrolled in -Reactnative | 19 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 3 | 0:07 | Passed
| Hide ongoing programs section when no ongoing program is available | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:11 | Passed
| Hide upcoming programs section when no upcoming program is available | 27 | 0 | 0 | 0 | 0 | 27 | 3 | 0 | 3 | 0:08 | Passed
| Open programs screen with no program | 45 | 0 | 0 | 0 | 0 | 54 | 6 | 0 | 6 | 0:14 | Passed
| Open Programs - Program Card for Ongoing program user has not enrolled in | 39 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 3 | 0:11 | Passed
| Open Programs - Program Card for Upcoming program user has not enrolled in | 33 | 0 | 0 | 0 | 0 | 33 | 3 | 0 | 3 | 0:11 | Passed
| Closed program -Reactnative | 21 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 3 | 0:08 | Passed
|  | 590 | 20 | 86 | 0 | 0 | 862 | 84 | 16 | 100 | 3:29 | 26
|  | 78.45% | 5.92% | 15.64% | 0% | 0% |  | 84% | 16% |  |  | 83.92%

## Reports_iOS
Intersert Survey | Date: 29/07/2022
| Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Navigation to Interest Survey screen | 7 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 1 | 0:05 | Passed
| Interests survey topics for Adult when library has Axis360 subscription | 9 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 1 | 0:04 | Passed
| Update interests preference | 24 | 1 | 0 | 0 | 0 | 25 | 3 | 1 | 4 | 0:11 | Failed
| Reset interest survey when profile type is changed | 18 | 0 | 0 | 0 | 0 | 18 | 2 | 0 | 2 | 0:08 | Passed
| Confirmation on changing profile type and message for reset of interest survey | 72 | 0 | 0 | 0 | 0 | 72 | 8 | 0 | 8 | 0:33 | Passed
| Interest survey cta in my profile screen | 21 | 2 | 4 | 0 | 0 | 27 | 1 | 2 | 3 | 0:07 | Failed
|  | 151 | 3 | 4 | 0 | 0 | 158 | 16 | 3 | 19 | 1:07 | 6
|  | 95.57% | 1.9% | 2.53% | 0% | 0% |  | 84.21% | 15.79% |  |  | 66.67%
Open Programs
Date: 02/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Hide ongoing programs section when no ongoing program is available | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:10 | Passed
| Hide upcoming programs section when no upcoming program is available | 27 | 0 | 0 | 0 | 0 | 27 | 3 | 0 | 3 | 0:08 | Passed
| Open programs screen with no program | 51 | 1 | 2 | 0 | 0 | 54 | 5 | 1 | 6 | 0:15 | Failed
| Open Programs - Program Card for Ongoing program user has not enrolled in | 33 | 1 | 5 | 0 | 0 | 39 | 2 | 1 | 3 | 0:12 | Failed
| Open Programs - Program Card for Upcoming program user has not enrolled in | 20 | 2 | 11 | 0 | 0 | 33 | 1 | 2 | 3 | 0:08 | Failed
|  | 155 | 4 | 18 | 0 | 0 | 177 | 14 | 4 | 18 | 0:53 | 5
|  | 87.57% | 2.26% | 10.17% | 0% | 0% |  | 77.78% | 22.22% |  |  | 40%
Open Programs
Date: 13/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Hide ongoing programs section when no ongoing program is available | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:10 | Passed
| Hide upcoming programs section when no upcoming program is available | 27 | 0 | 0 | 0 | 0 | 27 | 3 | 0 | 3 | 0:07 | Passed
| Open programs screen with no program | 54 | 0 | 0 | 0 | 0 | 54 | 6 | 0 | 6 | 0:14 | Passed
| Open Programs - Program Card for Ongoing program user has not enrolled in | 39 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 3 | 0:11 | Passed
| Open Programs - Program Card for Upcoming program user has not enrolled in | 33 | 0 | 0 | 0 | 0 | 33 | 3 | 0 | 3 | 0:11 | Passed
|  | 177 | 0 | 0 | 0 | 0 | 177 | 18 | 0 | 18 | 0:53 | 5
|  | 100% | 0% | 0% | 0% | 0% |  | 100% | 0% |  |  | 100%
My Programs
Date: 16/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Hide active programs section when no active program enrolled in -Reactnative | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:10 | Passed
| Hide closed programs section when no closed program for the user -Reactnative | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:08 | Passed
| My programs screen with no program -Reactnative | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:08 | Passed
| My Programs - Program Card for Upcoming program user has enrolled in -Reactnative | 24 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 3 | 0:10 | Passed
| Closed program -Reactnative | 21 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 3 | 0:07 | Passed
|  | 117 | 0 | 0 | 0 | 0 | 132 | 12 | 0 | 15 | 0:42 | 5
|  | 100% | 0% | 0% | 0% | 0% |  | 100% | 0% |  |  | 100%
Intersert Survey
Date: 13/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Navigation to Interest Survey screen | 7 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 1 | 0:05 | Passed
| Interests survey topics for Adult when library has Axis360 subscription | 7 | 1 | 1 | 0 | 0 | 9 | 0 | 1 | 1 | 0:05 | Failed
| Update interests preference | 23 | 2 | 0 | 0 | 0 | 25 | 2 | 2 | 4 | 0:14 | Failed
| Reset interest survey when profile type is changed | 15 | 1 | 2 | 0 | 0 | 18 | 1 | 1 | 2 | 0:08 | Failed
| Confirmation on changing profile type and message for reset of interest survey | 67 | 1 | 3 | 0 | 0 | 71 | 7 | 1 | 8 | 0:37 | Failed
| Interest survey cta in my profile screen | 18 | 3 | 6 | 0 | 0 | 27 | 0 | 3 | 3 | 0:07 | Failed
|  | 137 | 8 | 12 | 0 | 0 | 157 | 11 | 8 | 19 | 1:16 | 6
|  | 87.26% | 5.1% | 7.64% | 0% | 0% |  | 57.89% | 42.11% |  |  | 16.67%
Checkouts
Date: 13/08/2022
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| Adult user is able to View Checkout screen and titles based on profile | 60 | 0 | 0 | 0 | 0 | 60 | 5 | 0 | 5 | 0:16 | Passed
| Kid User is able to View Checkout screen and titles based on profile | 46 | 0 | 0 | 0 | 0 | 46 | 4 | 0 | 4 | 0:15 | Passed
| Teen user is able to View Checkout screen and titles based on profile | 39 | 2 | 5 | 0 | 0 | 46 | 4 | 0 | 4 | 0:14 | Passed
| View No titles in checkouts screen based on profile | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:10 | Passed
| Adult user is able to view sort options and sort titles on the Checkouts screen | 15 | 3 | 12 | 0 | 0 | 30 | 0 | 3 | 3 | 0:04 | Failed
|  | 184 | 5 | 17 | 0 | 0 | 206 | 16 | 3 | 19 | 0:59 | 5
|  | 89.32% | 2.43% | 8.25% | 0% | 0% |  | 73.68% | 26.32% |  |  | 60%
|  | Steps | [5 empty] | Scenarios |  |  | Features
| Feature | Passed | Failed | Skipped | Pending | Undefined | Total | Passed | Failed | Total | Duration | Status
| My Profile of Adult Patron | 6 | 0 | 0 | 0 | 0 | 23 | 2 | 0 | 2 | 0:02 | Passed
| Navigation to Interest Survey screen | 7 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 1 | 0:02 | Passed
| Interests survey topics for Adult when library has Axis360 subscription | 6 | 1 | 2 | 0 | 0 | 9 | 0 | 1 | 1 | 0:05 | Failed
| Update interests preference | 19 | 0 | 0 | 0 | 0 | 25 | 4 | 0 | 4 | 0:14 | Passed
| Reset interest survey when profile type is changed | 6 | 2 | 10 | 0 | 0 | 18 | 0 | 2 | 2 | 0:04 | Failed
| Confirmation on changing profile type and message for reset of interest survey | 52 | 2 | 17 | 0 | 0 | 71 | 6 | 2 | 8 | 0:21 | Failed
| Interest survey cta in my profile screen | 12 | 1 | 14 | 0 | 0 | 27 | 2 | 1 | 3 | 0:06 | Failed
| Adult user is able to View Checkout screen and titles based on profile | 42 | 3 | 15 | 0 | 0 | 60 | 2 | 3 | 5 | 0:07 | Failed
| Kid User is able to View Checkout screen and titles based on profile | 25 | 0 | 0 | 0 | 0 | 46 | 4 | 0 | 4 | 0:08 | Passed
| Teen user is able to View Checkout screen and titles based on profile | 40 | 1 | 5 | 0 | 0 | 46 | 3 | 1 | 4 | 0:09 | Failed
| View No titles in checkouts screen based on profile | 16 | 1 | 7 | 0 | 0 | 24 | 2 | 1 | 3 | 0:04 | Failed
| Adult user is able to view sort options and sort titles on the Checkouts screen | 15 | 0 | 0 | 0 | 0 | 30 | 3 | 0 | 3 | 0:04 | Passed
| Do not show quick navigation CTA for history screen | 33 | 2 | 15 | 0 | 0 | 50 | 8 | 2 | 10 | 0:07 | Failed
| View quick navigation CTAs for Checkouts, Holds, Wishlist, Recommendations, Checkout History and Downloads screen | 30 | 0 | 0 | 0 | 0 | 30 | 6 | 0 | 6 | 0:06 | Passed
| Filter titles on Checkouts, Holds, Wishlist, Recommended and Checkout History screen [TO BE UPDATED] | 24 | 0 | 0 | 0 | 0 | 45 | 5 | 0 | 5 | 0:08 | Passed
| Search within Checkouts, Holds, Recommendations, Wishlist, History and Downloads screen | 21 | 1 | 7 | 0 | 0 | 42 | 4 | 2 | 6 | 0:07 | Failed
| Hide active programs section when no active program enrolled in -Reactnative | 12 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:07 | Passed
| Hide closed programs section when no closed program for the user -Reactnative | 20 | 1 | 3 | 0 | 0 | 24 | 2 | 1 | 3 | 0:11 | Failed
| My programs screen with no program -Reactnative | 12 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:08 | Passed
| My Programs - Program Card for Upcoming program user has enrolled in -Reactnative | 19 | 2 | 4 | 0 | 0 | 39 | 2 | 1 | 3 | 0:07 | Failed
| Hide ongoing programs section when no ongoing program is available | 24 | 0 | 0 | 0 | 0 | 24 | 3 | 0 | 3 | 0:11 | Passed
| Hide upcoming programs section when no upcoming program is available | 27 | 0 | 0 | 0 | 0 | 27 | 3 | 0 | 3 | 0:08 | Passed
| Open programs screen with no program | 48 | 2 | 4 | 0 | 0 | 54 | 4 | 2 | 6 | 0:14 | Failed
| Open Programs - Program Card for Ongoing program user has not enrolled in | 39 | 0 | 0 | 0 | 0 | 39 | 3 | 0 | 3 | 0:11 | Passed
| Open Programs - Program Card for Upcoming program user has not enrolled in | 33 | 0 | 0 | 0 | 0 | 33 | 3 | 0 | 3 | 0:11 | Passed
| Closed program -Reactnative | 21 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 3 | 0:08 | Passed
|  | 609 | 19 | 103 | 0 | 0 | 862 | 81 | 19 | 100 | 3:29 | 26
|  | 73.45% | 8.92% | 17.64% | 0% | 0% |  | 81% | 19% |  |  | 79.92%